## Sheet1
Description | Likelihood | Impact | Mitigation Plan | Contributor Name | Date | Description
Familiarity with chosen framework and languages | 5 | 2 | Learn new tech within the second sprint to descent familiarity | Evan | 2017-09-09 | Risks 1-4
Inaccuracies in learner prediction suggestions | 5 | 5 | Dedicate more resources to studying algorithms and in implementation | Matthew | 2017-09-11 | Risk 5-7
Web scraping | 5 | 5 | Use previously known information along with already existing code to customize our algorithms to what we need | Brandon | 2017-09-13 | Risks 8 - 10
Front End/Back End integration | 3 | 2 | Have regular group meetings to ensure our integration works well | Matthew | 2017-09-14 | Final Changes/Updated Wording
Back End Component Integration | 4 | 4 | Use built in libraries within symfony to allow for many different back end components
App Development Issues | 3 | 3 | Allow for Joseph to lead the mac development and Erik with android because of previous knowledge
API integration issues | 2 | 3 | Research techniques that have been used within symfony by previous developers and best integrate to our design
Updates slowing down website | 3 | 3 | Implement an efficient storage technique and optimize algorithms to do updates faster
User Model Storage | 1 | 4 | Design our models to allow for scalability
Attributes don’t map nicely for products | 2 | 4 | Design our mapping algorithm to best map the attributes we need