## Sheet1
Description | Likelihood | Impact | Mitigation Plan | Contributor Name | Date | Description
Familiarity with chosen framework and languages | 3 | 2 | Over Sprint 2 we were able to become more familiar with the technology we chose to use
Web scraping | 3 | 5 | Brandon was able to make very good progress with this. We will now begin testing, however the likelihood has gone down.
Front End/Back End integration | 3 | 2 | Have regular group meetings to ensure our integration works well
Back End Component Integration | 0 | 4 | We removed symfony and used node. This risk was mitigated.
API integration issues | 0 | 3 | We were able to setup the API and it is now functioning
Attributes don’t map nicely for products | 2 | 4 | We believe using clarifai with the amazon website description we can mitigate this risk
Setting up channels using top tags | 2 | 5 | Integrating the clarifai solution should allow for us to have more general and common tags. In addition, using the amazon categories we should have a good base for channels
Setting up the database to be able to be accessed anywhere | 1 | 2 | Erik has familiarity with doing this type of solution, therefore he can help with any issues we have.
Suggestion Algorithm Implementation | 4 | 5 | We have been doing research on predesigned solutions that we can use as a basis for ours. We can continue this in Sprint 3.