## Sheet1
Description | Likelihood | Impact | Mitigation Plan | Contributor Name | Date | Description
Familiarity with chosen framework and languages | 2 | 2 | Over Sprint 3 we have gotten even more familiar with the languages and most team members are feeling very comfortable
Web scraping | 1 | 5 | Brandon has just about everything running and we are now pulling data.
Front End/Back End integration | 2 | 2 | We have our routing setup and the front and back end are collaborating fine using the API
Attributes don’t map nicely for products | 2 | 4 | We have succesfully used clarifia to grab tags, however the amazon tags can be hit or miss
Setting up channels using top tags | 2 | 5 | Integrating the clarifai solution should allow for us to have more general and common tags. In addition, using the amazon categories we should have a good base for channels. This risk is still ongoing and we plan to start addressing it in Sprint 3 and 4
Setting up the database to be able to be accessed anywhere | 0 | 2 | Erik has succesfully set up this function
Suggestion Algorithm Implementation | 4 | 5 | We have been doing research on predesigned solutions that we can use as a basis for ours. This risk will continue to be explored in this sprint and sprint 4 as we start to set it up
Domain Name Set up | 1 | 3 | Our server is set up already, therefore it should not be terribly difficult to set up our domain name
Loading data from the scraper into the database | 2 | 4 | We have started collecting data with the scraper, therefore we need to load this into the data. We have a fairly good idea on how to do this, therefore working together using our previous knowledge should be sufficient to mitigate this risk.