## Sheet1
Description | Likelihood | Impact | Mitigation Plan | Contributor Name | Date | Description
Familiarity with chosen framework and languages | 1 | 2 | This has been downgraded to a one because our group has a good handle on the languages chosen.
Web scraping | 0 | 5 | We have pulled all the data and cleaned some of the tags.
Front End/Back End integration | 1 | 2 | We have our routing setup and the front and back end are collaborating fine using the API
Attributes don’t map nicely for products | 2 | 4 | The tags from clarifai can be good at times, but sometimes they are not as good. We are in the process of cleaning the tags.
Setting up channels using top tags | 2 | 5 | We have began the process of picking the top tags that are viable for channels. This could still be a problem moving forward, however it appears that we have a decent handle on it.
Setting up the database to be able to be accessed anywhere | 1 | 2 | This seemed to have been solved, however there seems to be some compatiblity problems with certain types of inserts. We plan to see how to change our queries in Sprint 4.
Suggestion Algorithm Implementation | 4 | 5 | Some initial research has been done in Sprint 3. We are moving on to stage 1 of our suggestion algorithm. We plan to try and add some machine learning this sprint and see what risks may affect us moving forward.
Domain Name Set up | 0 | 3 | Domain name is in place now. The problem resides in the database that is on our server.
Loading data from the scraper into the database | 3 | 4 | We loaded the data in our local databases, however there is a problem with the database hosted on our server. We plan to modify the insert statements to see if this will fix it.
Data privacy | 1 | 2 | When a Shopper is followed, we want to make sure they are okay with other Shoppers seeing the products they like. We plan to implement a hide feature, but this could be a problem.
Creation of a mobile app | 3 | 3 | We are considering making a mobile application. This could take our focus off of our website and may not end up working. We plan to do some research on how easily we can hook our app up to our API to save work.